## Plan_Actual_Hour
No | Function Group | Plan (Hrs) | Actual (Hrs) | Variance | Status
1 | Project Setup & Planning | 16 | 16 | 0 | Completed
2 | Database Design & EF Models | 20 | 22 | 2 | Completed
3 | Backend API - Rooms & Zones | 16 | 18 | 2 | Completed
4 | Backend API - Booking | 20 | 24 | 4 | Completed
5 | Backend API - Services & Tours | 12 | 12 | 0 | Completed
6 | Backend API - Contact & FAQ | 8 | 8 | 0 | Completed
7 | Frontend - Home & Navigation | 16 | 16 | 0 | Completed
8 | Frontend - Room Categories & Detail | 20 | 22 | 2 | Completed
9 | Frontend - Booking Calendar UI | 24 | 28 | 4 | Completed
10 | Frontend - Checkout & Confirmation | 16 | 18 | 2 | Completed
11 | Frontend - Services & Tours Pages | 12 | 12 | 0 | Completed
12 | Frontend - Contact, FAQ, Gallery | 12 | 12 | 0 | Completed
13 | API Integration | 20 | 22 | 2 | Completed
14 | Docker Deployment | 12 | 14 | 2 | Completed
15 | Testing & Bug Fixes | 20 | 24 | 4 | Completed
16 | Documentation | 24 | 28 | 4 | Completed
17 | Code Review | 12 | 14 | 2 | Completed
18 | Meetings & Communication | 20 | 20 | 0 | Completed
| TOTAL | 300 | 330 | 30 | Completed

## By_Team_Member
No | Thành viên | Role | Plan (Hrs) | Actual (Hrs) | Variance
1 | Nguyễn Hoàng Dũng | PO / PM / Fullstack | 60 | 68 | 8
2 | Nguyễn Xuân Hiếu | SM / BA / Tester | 52 | 58 | 6
3 | Đặng Gia Khánh | Backend Lead | 52 | 58 | 6
4 | Nguyễn Thành Trung | Backend Dev | 44 | 46 | 2
5 | Phạm Công Khánh | Frontend Lead | 52 | 58 | 6
6 | Bùi Trần Hoàng Huy | Frontend Dev | 40 | 42 | 2

## Overtime_Detail
Ngày | Thứ | Loại | Giờ OT | Người tham gia
21/12 | T7 | Weekend | 6 | G.Khánh, Trung, C.Khánh
22/12 | CN | Weekend | 4 | G.Khánh, Trung
25/12 | Lễ | Holiday | 2 | C.Khánh, Hiếu
27/12 | T6 | Weekday | 4 | C.Khánh, Huy
28/12 | T7 | Weekend | 9 | Hiếu, C.Khánh, G.Khánh
29/12 | CN | Weekend | 10 | Hiếu, G.Khánh, Trung, C.Khánh, Huy
04/01 | T7 | Weekend | 4 | C.Khánh, Trung
05/01 | CN | Weekend | 9 | Hiếu, Huy, G.Khánh
07/01 | T2 | Weekday | 8 | C.Khánh, G.Khánh, Huy, Hiếu