## 2. SPRINT METRICS
Metric | Planned | Actual
Duration | 7 days | 7 days
Story Points | 25 | 25
Velocity | - | 25
Completion | 100% | 100%

## 3. SPRINT BACKLOG
ID | Task | Story | Assignee | Est (h) | Status
T-037 | Setup Docker Compose | US-017 | Nguyễn Hoàng Dũng | 3 | ✅ Done
T-038 | Configure Nginx reverse proxy | US-017 | Nguyễn Hoàng Dũng | 2 | ✅ Done
T-039 | Build production containers | US-017 | Nguyễn Hoàng Dũng | 2 | ✅ Done
T-040 | Deploy and test Docker | US-017 | Nguyễn Hoàng Dũng | 2 | ✅ Done
T-041 | Convert ContactUs.tsx to API | US-018 | Bùi Trần Hoàng Huy | 3 | ✅ Done
T-042 | Implement contact form submission | US-018 | Bùi Trần Hoàng Huy | 2 | ✅ Done
T-043 | Convert ServicesEvents.tsx to API | US-019 | Phạm Công Khánh | 3 | ✅ Done
T-044 | Add service booking form | US-019 | Phạm Công Khánh | 2 | ✅ Done
T-045 | Convert FAQView.tsx to API | US-020 | Bùi Trần Hoàng Huy | 2 | ✅ Done
T-046 | Convert ExperiencesTours.tsx to API | US-021 | Phạm Công Khánh | 3 | ✅ Done
T-047 | Add tour booking form | US-021 | Phạm Công Khánh | 2 | ✅ Done
T-048 | Conduct code review | US-022 | Nguyễn Hoàng Dũng | 4 | ✅ Done
T-049 | Fix code review issues | US-022 | All Team | 2 | ✅ Done
T-050 | Write test cases | US-023 | Nguyễn Xuân Hiếu | 4 | ✅ Done
T-051 | Execute final testing | US-023 | Nguyễn Xuân Hiếu | 4 | ✅ Done
T-052 | Write User Guide | US-024 | Nguyễn Xuân Hiếu | 4 | ✅ Done
T-053 | Complete all documentation | US-024 | Nguyễn Xuân Hiếu | 3 | ✅ Done

## 5. DAILY PROGRESS
Day | Tasks Done | Points | Notes
02/01 | T-037, T-038 | 3 | Docker setup - Nguyễn Hoàng Dũng
03/01 | T-039, T-040, T-041 | 4 | Docker done + ContactUs
04/01 | T-042, T-043, T-044 | 4 | Forms + ServicesEvents
05/01 | T-045, T-046, T-047 | 4 | FAQ + Tours done
06/01 | T-048, T-049 | 4 | Code Review - All team
07/01 | T-050, T-051 | 4 | Testing - Nguyễn Xuân Hiếu
08/01 | T-052, T-053 | 4 | Documentation complete

## Team contributions
Member | Tasks | Points
Nguyễn Hoàng Dũng (PO) | T-037 to T-040, T-048 | 8
Phạm Công Khánh (FE Lead) | T-043, T-044, T-046, T-047 | 6
Bùi Trần Hoàng Huy (FE) | T-041, T-042, T-045 | 4
Nguyễn Xuân Hiếu (SM/Tester) | T-050 to T-053 | 9
Đặng Gia Khánh (BE Lead) | Support, bug fixes | -
Nguyễn Thành Trung (BE) | Support, bug fixes | -

## 7. FINAL PROJECT STATUS
Metric | Value
**Total Story Points** | 75
**Completed** | 75 (100%)
**Total Sprints** | 3
**Total Duration** | 21 days
**Team Size** | 6 members