# GANTT CHART REPORT

## The Wandering Rose - Villa Booking System

## 1. TỔNG QUAN TIẾN ĐỘ

| Thông tin | Chi tiết |
| --- | --- |
| Ngày bắt đầu | 19/12/2025 |
| Ngày kết thúc | 08/01/2026 |
| Tổng thời gian | 21 ngày |
| Số Sprint | 3 |
| Trạng thái | ✅ Hoàn thành 100% |

## 2. GANTT CHART - TỔNG QUAN (3 SPRINTS)

TASK                          |Dec 19-25    |Dec 26-31    |Jan 02-08    |
                              |SPRINT 1     |SPRINT 2     |SPRINT 3     |
                              |Backend      |API Integ    |Deploy       |
──────────────────────────────┼─────────────┼─────────────┼─────────────┤
SPRINT 1: BACKEND SETUP       |             |             |             |
├─ Analyze React project      |████         |             |             |
├─ Create implementation plan |████         |             |             |
├─ Define 13 EF models        |  ██████     |             |             |
├─ Configure DbContext        |    ████     |             |             |
├─ Generate EF migration      |      ██     |             |             |
├─ Create database seeder     |      ████   |             |             |
├─ Seed data from constants   |        ████ |             |             |
├─ Analyze Figma & Export     |          ██ |             |             |
└─ Create useApi.ts hooks     |          ██ |             |             |
                              |             |             |             |
SPRINT 2: API INTEGRATION     |             |             |             |
├─ Add CORS configuration     |             |██           |             |
├─ Add .env configuration     |             |██           |             |
├─ Implement 9 Controllers    |             |████████     |             |
├─ Create api.ts service      |             |    ████     |             |
├─ Convert HomeView to API    |             |      ████   |             |
├─ Convert RoomCategories     |             |        ████ |             |
└─ Build Booking Calendar     |             |        ████ |             |
                              |             |             |             |
SPRINT 3: DEPLOYMENT          |             |             |             |
├─ Deploy to Docker           |             |             |██████       |
├─ Convert ContactUs          |             |             |  ████       |
├─ Convert ServicesEvents     |             |             |    ████     |
├─ Convert FAQ & Tours        |             |             |      ████   |
├─ Code Review                |             |             |        ████ |
├─ Execute Final Testing      |             |             |          ██ |
└─ Write Documentation        |             |             |          ██ |
──────────────────────────────┴─────────────┴─────────────┴─────────────┘
                              25/12         31/12         08/01
                              Sprint 1      Sprint 2      Sprint 3
                              Review        Review        Review

🎄 01/01/2026 = Nghỉ Tết Dương lịch

## 3. MILESTONE 1 REPORT (25/12/2025 - Sprint 1 Review)

### 3.1 Planned vs Actual

| Deliverable | Planned | Actual | Status |
| --- | --- | --- | --- |
| Analyze React project | 21/12 | 20/12 | ✅ Early |
| Implementation plan | 21/12 | 20/12 | ✅ Early |
| 13 EF Models | 23/12 | 22/12 | ✅ Early |
| DbContext + Migration | 24/12 | 23/12 | ✅ Early |
| Database Seeder | 24/12 | 24/12 | ✅ On time |
| useApi.ts hooks | 25/12 | 25/12 | ✅ On time |

### 3.2 Sprint 1 Metrics

| Metric | Value |
| --- | --- |
| Planned Story Points | 25 |
| Completed Story Points | 25 |
| Velocity | 25 points |
| Completion Rate | 100% |

## 4. MILESTONE 2 REPORT (31/12/2025 - Sprint 2 Review)

### 4.1 Planned vs Actual

| Deliverable | Planned | Actual | Status |
| --- | --- | --- | --- |
| CORS + .env | 27/12 | 26/12 | ✅ Early |
| 9 Controllers | 29/12 | 28/12 | ✅ Early |
| api.ts service | 30/12 | 29/12 | ✅ Early |
| HomeView API | 30/12 | 30/12 | ✅ On time |
| RoomCategories API | 31/12 | 30/12 | ✅ Early |
| Booking Calendar | 31/12 | 31/12 | ✅ On time |

### 4.2 Sprint 2 Metrics

| Metric | Value |
| --- | --- |
| Planned Story Points | 25 |
| Completed Story Points | 25 |
| Velocity | 25 points |
| Completion Rate | 100% |

## 5. FINAL MILESTONE REPORT (08/01/2026 - Sprint 3 Review)

### 5.1 Final Delivery Status

| Deliverable | Status |
| --- | --- |
| ✅ Docker Deployment | Production ready |
| ✅ All Pages API connected | 4 pages converted |
| ✅ Code Review | Completed with fixes |
| ✅ Testing | 23 test cases passed |
| ✅ Documentation | Complete |

### 5.2 Sprint 3 Metrics

| Metric | Value |
| --- | --- |
| Planned Story Points | 25 |
| Completed Story Points | 25 |
| Velocity | 25 points |
| Completion Rate | 100% |

## 6. PROJECT TOTALS

| Metric | Sprint 1 | Sprint 2 | Sprint 3 | Total |
| --- | --- | --- | --- | --- |
| Story Points | 25 | 25 | 25 | 75 |
| Duration | 7 days | 6 days | 7 days | 20 days |
| Bugs Found | 3 | 5 | 5 | 13 |
| Bugs Fixed | 3 | 5 | 5 | 13 |
| Test Cases | 8 | 7 | 8 | 23 |

## 7. EVM SUMMARY

| Metric | Sprint 1 | Sprint 2 | Sprint 3 | Final |
| --- | --- | --- | --- | --- |
| PV | 25 pts | 50 pts | 75 pts | 75 pts |
| EV | 25 pts | 50 pts | 75 pts | 75 pts |
| SPI | 1.00 | 1.00 | 1.00 | 1.00 |
| Status | ✅ | ✅ | ✅ | ✅ On schedule |

## 8. LESSONS LEARNED

| Category | Lesson |
| --- | --- |
| Planning | Chia 3 sprints giúp quản lý workload tốt hơn |
| Backend | EF Core migration cần test kỹ trước khi deploy |
| API | CORS cần config đúng từ đầu |
| Deployment | Docker giúp deployment nhất quán |
| Teamwork | Daily standup quan trọng để sync progress |

Phiên bản: 3.0 | Ngày cập nhật: 15/01/2026 Người lập: Nguyễn Xuân Hiếu (Scrum Master)