## Thời gian 2000 - 2015 ¦ Faci
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Analyze React project | Implementation plan | None
Nguyễn Xuân Hiếu (SM) | Setup Trello board | Facilitate standups | None
Đặng Gia Khánh (BE Lead) | Study EF Core | Define User, Villa models | None
Nguyễn Thành Trung (BE) | Review database design | Support EF models | None
Phạm Công Khánh (FE Lead) | Review Figma design | Start asset export | None
Bùi Trần Hoàng Huy (FE) | Study React hooks | Prepare useApi.ts | None

## Thời gian 2000 - 2015 ¦ F_2
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Review EF models | Check migration | None
Nguyễn Xuân Hiếu (SM) | Track burndown | Update progress | None
Đặng Gia Khánh (BE Lead) | Complete 13 models | Configure DbContext | None
Nguyễn Thành Trung (BE) | Help with models | Create seeder class | None
Phạm Công Khánh (FE Lead) | Export Figma assets | Complete export | None
Bùi Trần Hoàng Huy (FE) | Study API patterns | Start useApi.ts | None

## Thời gian 2000 - 2015 ¦ F_3
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Review seeder | Sprint 1 review prep | None
Nguyễn Xuân Hiếu (SM) | Progress OK | Sprint 1 review | None
Đặng Gia Khánh (BE Lead) | Seed data done | Present backend work | None
Nguyễn Thành Trung (BE) | Test seeder | Demo database | None
Phạm Công Khánh (FE Lead) | Assets ready | Present Figma work | None
Bùi Trần Hoàng Huy (FE) | useApi.ts done | Demo hooks | None

## Thời gian 2000 - 2015 ¦ F_4
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Setup .env config | Review controllers | None
Nguyễn Xuân Hiếu (SM) | Start Sprint 2 | Track progress | None
Đặng Gia Khánh (BE Lead) | RoomsController | ZonesController, BookingsController | None
Nguyễn Thành Trung (BE) | CORS configuration | VillasController | None
Phạm Công Khánh (FE Lead) | Review api.ts | Start HomeView conversion | None
Bùi Trần Hoàng Huy (FE) | Create api.ts | Support API integration | None

## Thời gian 2000 - 2015 ¦ F_5
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | All controllers reviewed | Prepare Sprint 2 review | None
Nguyễn Xuân Hiếu (SM) | Burndown healthy | Sprint 2 review prep | None
Đặng Gia Khánh (BE Lead) | All controllers done | Support FE integration | None
Nguyễn Thành Trung (BE) | Controllers complete | Test API endpoints | None
Phạm Công Khánh (FE Lead) | HomeView converted | RoomCategories conversion | None
Bùi Trần Hoàng Huy (FE) | api.ts complete | Booking Calendar UI | None

## Thời gian 2000 - 2015 ¦ F_6
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Review all features | Sprint 2 review | None
Nguyễn Xuân Hiếu (SM) | Track final progress | Conduct review | None
Đặng Gia Khánh (BE Lead) | Support integration | Demo API | None
Nguyễn Thành Trung (BE) | API tested | Demo endpoints | None
Phạm Công Khánh (FE Lead) | RoomCategories done | Demo UI pages | None
Bùi Trần Hoàng Huy (FE) | Calendar UI done | Demo booking flow | None

## Thời gian 2000 - 2015 ¦ F_7
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Docker setup | Complete Docker deployment | None
Nguyễn Xuân Hiếu (SM) | Post-holiday sync | Track Sprint 3 | None
Đặng Gia Khánh (BE Lead) | Support Docker | Help with config | None
Nguyễn Thành Trung (BE) | Review Docker | Test containers | None
Phạm Công Khánh (FE Lead) | Holiday | ServicesEvents page | None
Bùi Trần Hoàng Huy (FE) | Holiday | ContactUs page | None

## Thời gian 2000 - 2015 ¦ F_8
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | All pages reviewed | Code review | None
Nguyễn Xuân Hiếu (SM) | Track progress | Start testing | None
Đặng Gia Khánh (BE Lead) | Bug fixes | Support code review | None
Nguyễn Thành Trung (BE) | Bug fixes | Support code review | None
Phạm Công Khánh (FE Lead) | Tours page done | Fix code review issues | None
Bùi Trần Hoàng Huy (FE) | FAQ page done | Fix code review issues | None

## Thời gian 2000 - 2015 ¦ F_9
Thành viên | Hôm qua | Hôm nay | Blockers
Nguyễn Hoàng Dũng (PO) | Final review | Project delivery | None
Nguyễn Xuân Hiếu (SM) | Testing complete | Documentation done | None
Đặng Gia Khánh (BE Lead) | All fixes done | Final demo | None
Nguyễn Thành Trung (BE) | All fixes done | Final demo | None
Phạm Công Khánh (FE Lead) | All pages done | Final demo | None
Bùi Trần Hoàng Huy (FE) | All pages done | Final demo | None

## SUMMARY
# | Meeting | Date | Sprint | Key Discussion
1 | Standup 1 | 20/12 | Sprint 1 | EF Models progress
2 | Standup 2 | 23/12 | Sprint 1 | DbContext & Seeder
3 | Sprint 1 Review | 25/12 | Sprint 1 | Backend foundation complete
4 | Standup 3 | 27/12 | Sprint 2 | Controllers development
5 | Standup 4 | 30/12 | Sprint 2 | API Integration progress
6 | Sprint 2 Review | 31/12 | Sprint 2 | Core UI connected
7 | Standup 5 | 03/01 | Sprint 3 | Docker deployment
8 | Standup 6 | 06/01 | Sprint 3 | Code review & Testing
9 | Sprint 3 Review | 08/01 | Sprint 3 | Final delivery