## 1. RISK SUMMARY
Metric | Value
**Tổng số rủi ro** | 12
**Critical** | 2
**High** | 3
**Medium** | 5
**Low** | 2

## 2. RISK REGISTER TABLE
ID | Rủi ro | Category | Prob | Impact | Score | Response | Owner | Status
R01 | **Timeline quá ngắn** (21 ngày) | Schedule | 3 | 3 | **9** | Mitigate: Ưu tiên MVP, không scope creep | SM (B) | ✅ Closed
R02 | **Integration frontend-backend fail** | Technical | 2 | 3 | **6** | Mitigate: API contract sớm, mock data | D, E | ✅ Closed
R03 | **Thiếu kinh nghiệm Scrum** | Resource | 2 | 2 | **4** | Mitigate: SM coaching, daily standup | SM (B) | ✅ Closed
R04 | **Yêu cầu thay đổi giữa chừng** | Scope | 2 | 2 | **4** | Accept: Change management process | PO (A) | ✅ Closed
R05 | **Calendar picker phức tạp** | Technical | 3 | 2 | **6** | Mitigate: Allocate thêm thời gian | C | ✅ Closed
R06 | **Team member nghỉ không báo** | Resource | 2 | 2 | **4** | Mitigate: Cross-training, pair programming | SM (B) | ⚪ Open
R07 | **Scope creep** | Scope | 2 | 2 | **4** | Avoid: No changes during Sprint | PO (A) | ✅ Closed
R08 | **Code quality kém** | Quality | 2 | 2 | **4** | Mitigate: Code review bắt buộc | All | ✅ Closed
R09 | **Testing không đủ** | Quality | 2 | 2 | **4** | Mitigate: 20+ test cases required | F | ✅ Closed
R10 | **Documentation thiếu** | Process | 2 | 1 | **2** | Accept: Allocate time cuối project | A, B | ✅ Closed
R11 | **Docker/deployment issues** | Technical | 2 | 1 | **2** | Mitigate: Test locally trước | E | ✅ Closed
R12 | **Nghỉ lễ 01/01** ảnh hưởng tiến độ | Schedule | 3 | 2 | **6** | Accept: Plan around holidays | SM (B) | ✅ Closed

## R01 Timeline quá ngắn
Attribute | Value
**Mô tả** | Dự án chỉ có 21 ngày, rất ngắn cho full-stack app
**Trigger** | Không hoàn thành Sprint commitments
**Impact** | Không delivery đúng hạn, điểm thấp
**Mitigation** | Focus MVP, không thêm features, tăng work hours nếu cần
**Status** | ✅ Closed - Delivered on time

## R02 Integration Issues
Attribute | Value
**Mô tả** | Frontend và Backend không kết nối được
**Trigger** | API errors, CORS issues
**Impact** | App không hoạt động end-to-end
**Mitigation** | Define API contract sớm, mock controller cho dev
**Status** | ✅ Closed - Integration thành công

## R05 Calendar Picker Phức Tạp
Attribute | Value
**Mô tả** | Custom calendar picker khó hơn dự kiến
**Trigger** | Complex date logic, UX requirements
**Impact** | Booking flow bị delay
**Mitigation** | Pair programming, extra 2 days buffer
**Status** | ✅ Closed - Completed with minor delay

## R12 Nghỉ lễ 0101
Attribute | Value
**Mô tả** | Mất 1 ngày do nghỉ Tết Dương lịch
**Trigger** | National holiday
**Impact** | Giảm capacity Sprint 2
**Mitigation** | Factor in khi planning, tăng effort các ngày khác
**Status** | ✅ Closed - Compensated

## 5. LESSONS LEARNED
Risk | Lesson
R01 | Luôn có buffer time cho unexpected issues
R02 | API contract trước khi dev là quan trọng
R05 | UI components phức tạp cần estimate cao hơn
R12 | Factor holidays vào planning