# SCHEDULE BASELINE

## The Wandering Rose - Villa Booking System

## 1. GANTT CHART OVERVIEW

### Timeline: 19/12/2025 - 08/01/2026 (21 ngày)

Week 1 (19-25/12)    Week 2 (26/12-01/01)    Week 3 (02-08/01)
|----Sprint 1--------|-----------|--------Sprint 2----------|
     ████████████████████████        ███████████████████████

## 2. CHI TIẾT GANTT CHART

### SPRINT 1 (19/12 - 29/12/2025)

| Task | Người | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint Planning | All | ██ |  |  |  |  |  |  |  |  |  |  |
| Project Setup | C, E | ██ | ██ |  |  |  |  |  |  |  |  |  |
| Database Design | E |  | ██ | ██ | ██ |  |  |  |  |  |  |  |
| API Setup | D, E |  |  | ██ | ██ | ██ |  |  |  |  |  |  |
| Home Page | C |  |  | ██ | ██ | ██ |  |  |  |  |  |  |
| Room Categories | C |  |  |  |  | ██ | ██ | ██ |  |  |  |  |
| Room Detail | C |  |  |  |  |  | ██ | ██ | ██ |  |  |  |
| Booking Calendar | C, D |  |  |  |  |  |  | ██ | ██ | ██ |  |  |
| Testing Sprint 1 | F |  |  |  |  |  |  |  |  | ██ | ██ |  |
| Sprint Review | All |  |  |  |  |  |  |  |  |  |  | ██ |

### SPRINT 2 (30/12 - 08/01/2026)

| Task | Người | 30 | 31 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint Planning | All | ██ |  |  |  |  |  |  |  |  |  |
| Checkout Flow | C, D | ██ | ██ | 🎄 | ██ |  |  |  |  |  |  |
| Payment View | C |  |  | 🎄 | ██ | ██ |  |  |  |  |  |
| Confirmation | C |  |  | 🎄 |  | ██ | ██ |  |  |  |  |
| Services Page | C |  |  | 🎄 |  |  | ██ | ██ |  |  |  |
| Tours Page | C |  |  | 🎄 |  |  |  | ██ | ██ |  |  |
| Contact & FAQ | C, D |  |  | 🎄 |  |  |  |  | ██ | ██ |  |
| Integration Test | F, E |  |  | 🎄 |  |  |  |  | ██ | ██ |  |
| Bug Fixes | All |  |  | 🎄 |  |  |  |  |  | ██ | ██ |
| Documentation | A, B |  |  | 🎄 |  |  |  |  |  | ██ | ██ |
| Final Review | All |  |  |  |  |  |  |  |  |  | ██ |

🎄 = Nghỉ Tết Dương lịch (01/01/2026)

## 3. MILESTONES

| # | Milestone | Ngày | Status |
| --- | --- | --- | --- |
| M0 | Project Kickoff | 19/12/2025 | ✅ Completed |
| M1 | Sprint 1 Review | 29/12/2025 | ✅ Completed |
| M2 | Sprint 2 Review | 08/01/2026 | ✅ Completed |
| M3 | Final Delivery | 08/01/2026 | ✅ Completed |

## 4. CRITICAL PATH

graph LR
    A[Project Setup] --> B[Database Design]
    B --> C[API Setup]
    C --> D[Room Pages]
    D --> E[Booking Calendar]
    E --> F[Checkout Flow]
    F --> G[Payment/Confirm]
    G --> H[Testing]
    H --> I[Final Delivery]

Đường găng (Critical Path): Setup → Database → API → Rooms → Booking → Checkout → Testing → Delivery

Tổng thời gian: 21 ngày (không có float time)

## 5. RESOURCE ALLOCATION

| Thành viên | Sprint 1 Focus | Sprint 2 Focus |
| --- | --- | --- |
| A (PO) | Backlog mgmt | Review, Docs |
| B (SM) | Process, Standup | Process, Docs |
| C (Dev) | Frontend core | Frontend remaining |
| D (Dev) | Backend API | Backend, Integration |
| E (Dev) | Database, API | Integration |
| F (Tester) | Test S1 features | Test S2, Final |

## 6. BUFFER TIME

| Loại | Thời gian |
| --- | --- |
| Sprint 1 Buffer | 1 ngày (28/12 - testing day) |
| Sprint 2 Buffer | 1 ngày (07/01 - bug fix day) |
| Total Buffer | 2 ngày (~10% of 21 days) |

Phiên bản: 1.0 | Ngày tạo: 19/12/2025